## Sheet1
ROADS
Table 21.6-ACHIEVEMENTS OF NATIONAL HIGHWAYS DEVELOPMENT PROJECTS & OTHER PROJECTS
`
NHDP components | Total Length (km) | Competed 4/6 Lane '(km) | Under implementation Length (km) No. of Contracts |  | Balance for Award of Civil Work (km)
1 | 2 | 3 | 4 | 5 | 6
(As on 31 July,2015)
GQ | 5846 | 5846 | 0 | 0 | 0
NS-EW | 7142 | 6394 | 399 | 37 | 349
Port Connectivity | 380 | 379 | 1 | 1 | 0
Other NHs | 1768 | 1489 | 279 | 10 | 0
SARDP-NE | 112* | 105 | 7 | 1 | 0
NHDP Phase III | 12109 | 6594 | 3021 | 80 | 2494
NHDP Phase IV | 20000 | 2058 | 7027 | 73 | 10915
NHDP Phase V | 6500 | 2216 | 1465 | 23 | 2820
NHDP Phase VI | 1000 | 0 | 0 | 0 | 1000
NHDP Phase VII | 700 | 22 | 19 | 1 | 659
Total | 55445 | 25103 | 12218 | 226 | 18237
* - 278 km length transferred to NHIDCL
(As on 31 October,2014)
GQ | 5846 | 5846 | 0 | 0 | -
NS-EW | 7142 | 6325 | 400 | 45 | 417
Port Connectivity | 380 | 379 | 1 | 1 | 0
Other NHs | 1754 | 1408 | 346 | 10 | -
SARDP-NE | 388 | 95 | 16 | 1 | 277
NHDP Phase III | 12109 | 6300 | 4464 | 89 | 1345
NHDP Phase IV | 14799 | 776 | 5509 | 50 | 8514
NHDP Phase V | 6500 | 1919 | 2162 | 27 | 2419
NHDP Phase VI | 1000 | 0 | 0 | 0 | 1000
NHDP Phase VII | 700 | 22 | 19 | 1 | 659
Total | 50618 | 23070 | 12917 | 224 | 14631
(As on 31 May, 2013)
GQ | 5846 | 5846 | 0 | 6 | -
NS-EW | 7142 | 6155 | 615 | 53 | 372
Port Connectivity | 380 | 374 | 6 | 2 | 0
Other NHs | 1390 | 1146 | 224 | 4 | 20
SARDP-NE | 388 | 69 | 43 | 2 | 276
NHDP Phase III | 12109 | 5565 | 4859 | 89 | 1685
NHDP Phase IV | 14799 | 276 | 3999 | 32 | 10524
NHDP Phase V | 6500 | 1574 | 2506 | 28 | 2420
NHDP Phase VI | 1000 | 0 | 0 | 0 | 1000
NHDP Phase VII | 700 | 21 | 20 | 2 | 659
Total | 49328.5 | 21042 | 12330.5 | 221 | 15956
(As on December 31, 2012)
GQ | 5846 | 5846 | 0 | 8 | -
NS-EW | 7142 | 6053 | 722 | 59 | 367
Port Connectivity | 380 | 368 | 12 | 3 | 0
Other NHs | 1390 | 964 | 406 | 4 | 20
SARDP-NE | 388 | 49 | 63 | 2 | 276
NHDP Phase III | 12109 | 4602 | 5734 | 90 | 1773
NHDP Phase IV | 20000 | 62 | 4300 | 31 | 15638
NHDP Phase V | 6500 | 1276 | 2804 | 28 | 2420
NHDP Phase VI | 1000 | - | - | - | 1000
NHDP Phase VII | 700 | 19 | 22 | 2 | 659
Total | 55455 | 19239 | 14063 | 227 | 22153
(As on December 31, 2011)
GQ | 5846 | 5831 | 15 | 8 | ..
NS-EW | 7142 | 5914 | 803 | 76 | 420
Port Connectivity | 380 | 341 | 39 | 4 | -
Other NHs | 1390 | 946 | 424 | 5 | 20
SARDP-NE | 388 | 5 | 107 | 2 | 276
NHDP Phase III | 12109 | 3024 | 6514 | 90 | 2572
NHDP Phase IV | 20000 | .. | 2549 | 18 | 17451
NHDP Phase V | 6500 | 709 | 2768 | 22 | 3023
NHDP Phase VI | 1000 | .. | .. | .. | 1000
NHDP Phase VII | 700 | 7 | 41 | 2 | 659
Total | 55455 | 16777 | 13260 | 227 | 25421
(As on November 30, 2010)
GQ | 5846 | 5809 | 37 | 10 | ..
NS-EW | 7142 | 5385 | 1332 | 106 | 425
Port Connectivity | 380 | 291 | 83 | 6 | 6
Other NHs | 1383 | 926 | 437 | 7 | 20
SARDP-NE | 388 | .. | 112 | 2 | 276
NHDP Phase III | 12109 | 1922 | 5207 | 73 | 4980
NHDP Phase IV | 20000 | .. | 486 | 4 | 19514
NHDP Phase V | 6500 | 407 | 1893 | 16 | 4200
NHDP Phase VI | 1000 | .. | .. | .. | 1000
NHDP Phase VII | 700 | .. | 41 | 2 | 659
Total | 55448 | 14740 | 9628 | 226 | 31080
(As on November 30,2009
GQ | 5846 | 5743 | 103 | .. | ..
NS-EW | 7142 | 4439 | 2066 | .. | 637
Port Connectivity | 380 | 244 | 130 | .. | 6
Other NHs | 965 | 868 | 77 | .. | 20
NHDP Phase III | 12109 | 1089 | 2714 | .. | 8306
NHDP Phase V | 6500 | 148 | 886 | .. | 5466
NHDP Phase VII | 700 | .. | 19 | .. | 681
Total | 33642 | 12531 | 5995 | .. | 15116
( As on March 31,2009
GQ | 5846 | 5721 | 125 | .. | ..
NS-EW | 7142 | 3436 | 2915 | .. | 791
Port Connectivity | 380 | 206 | 168 | .. | 6
Other NHs | 962 | 781 | 161 | .. | 20
NHDP Phase III | 12109 | 787 | 1878 | .. | 9444
NHDP Phase V | 6500 | 106 | 928 | .. | 5470
NHDP Phase VII | 700 | .. | 19 | .. | 681
Total | 33639 | 11037 | 6194 | .. | 16412
( As on November 30,2007)
GQ | 5846 | 5629 | 217 | 25 | ..
NS-EW | 7300 | 1559 | 4762 | 148 | 821
Port Connectivity | 380 | 163 | 211 | 8 | 6
Other NHs | 962 | 337 | 605 | 16 | 20
NHDP Phase III | 12109 | 274 | 1801 | 32 | 10034
NHDP Phase V | 6500 | .. | 148 | 2 | 6352
NHDP Phase VII | .. | .. | .. | .. | ..
Total | 33097 | 7962 | 7944 | 231 | 17233
Source:-National Highways Authority of India
Notes :- GQ=Golden Quadilateral
NS-EW=North-South & East-West Corridor